## Members
Title |  |  | Backlog | Feature Group | Status | Owner | Capacity | Detail Estimate | To Do | ID | To Do | Dev Complete Planned Date | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08
Alston Meng | [6 empty] | 95.2 | 77 | 77
Alston Meng | 3 QA-Add question mark for Topic and answer Type |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397343 | 2
Alston Meng | 4 QA-Change lunch confirm dialog text from "Create" to "Lunch" |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397345 | 2
Alston Meng | 5 QA-change delete button in program image |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397346 | 2
Alston Meng | 6 QA-Add question mark for Mentoring Availability Title |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397347 | 2
Alston Meng | 7 QA-Button Text change (Start Signup changed to Join) |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397348 | 2
Alston Meng | 8 QA-Delete the description of “Select criteria that best match with your interests for your mentees” |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397349 | 2
Alston Meng | 10 QA-message change for choose mentor for supervised matching. |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397351 | 2
Alston Meng | 11 QA-Delete the description of“Select criteria that best match with your interests for your mentors.” And description change to “Describe your ideal mentor” replace “choose your proferences” |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397352 | 2
Alston Meng | 12 QA-Title Text change |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397353 | 2
Alston Meng | 15 QA-Use standard control for availability status (no text) |  | Fit&Finish |  |  | Haiyun Jiang |  | 2 | 2 | TK-397356 | 2
Alston Meng | QA - Test Design |  | [b1608 BUGATHON] Mentee Signup Form: Better to display mentor preferences but not matched area on mentor card. |  |  | Haiyun Jiang |  | 9 | 9 | TK-397769 | 9 | 2017-02-22
Alston Meng | QA - Test Execution |  | [b1608 BUGATHON] Mentee Signup Form: Better to display mentor preferences but not matched area on mentor card. |  |  | Haiyun Jiang |  | 18 | 18 | TK-397770 | 18 | 2017-02-22
Alston Meng | QA - Test Design |  | Create open-ended program in wizard |  |  | Alston Meng |  | 12 | 12 | TK-396766 | 12 | 2017-03-01
Alston Meng | QA - test execution |  | Create open-ended program in wizard |  |  | Alston Meng |  | 15 | 15 | TK-396767 | 15 | 2017-03-01
Alston Meng | QA - Test Design |  | Edit open-ended program in overview |  |  | Alston Meng |  | 12 | 12 | TK-396785 | 12 | 2017-03-01
Alston Meng | QA - Test Execution |  | Edit open-ended program in overview |  |  | Alston Meng |  | 18 | 18 | TK-396786 | 18 | 2017-03-01
Alston Meng | QA - Execution |  | Ad hoc report change for open-ended program |  |  | Alston Meng |  | 20 | 20 | TK-396912 | 20 | ?
Amy Chen | [6 empty] | 95.2 | 83 | 83
Amy Chen | QA - Design |  | Show the mentee/mentor card that a relationship is closed. |  |  | Amy Chen |  | 8 | 8 | TK-396823 | 8 | 2017-02-15
Amy Chen | QA - Execution |  | Show the mentee/mentor card that a relationship is closed. |  |  | Amy Chen |  | 12 | 12 | TK-396824 | 12 | 2017-02-15
Amy Chen | QA - Design |  | CDP-5831 Update Launch/Invitation/Start Date According to event happens date |  |  | Amy Chen |  | 9 | 9 | TK-396889 | 9 | ?
Amy Chen | QA - Execution |  | CDP-5831 Update Launch/Invitation/Start Date According to event happens date |  |  | Amy Chen |  | 15 | 15 | TK-396890 | 15 | ?
Amy Chen | QA - Design |  | [B1702][Primary key]Lack of blue primary button in overview page popup and wizard popup and poxy popup |  |  | Amy Chen |  | 9 | 9 | TK-396896 | 9 | 2017-02-13
Amy Chen | QA - Execution |  | [B1702][Primary key]Lack of blue primary button in overview page popup and wizard popup and poxy popup |  |  | Amy Chen |  | 9 | 9 | TK-396897 | 9 | 2017-02-13
Amy Chen | QA - Design |  | [b1702 BUGATHON]Wizard Summary Page: 3 scroll bars on page |  |  | Amy Chen |  | 1 | 1 | TK-396934 | 1 | ?
Amy Chen | QA - Execution |  | [b1702 BUGATHON]Wizard Summary Page: 3 scroll bars on page |  |  | Amy Chen |  | 3 | 3 | TK-396935 | 3 | ?
Amy Chen | QA - Design |  | i18n defects engineered by wrong use of parameters: DEVELOPMENT_MENTORING_SELECT_HINT=Select or type a {0}... |  |  | Amy Chen |  | 3 | 3 | TK-397210 | 3 | 2017-02-17
Amy Chen | QA - Execution |  | i18n defects engineered by wrong use of parameters: DEVELOPMENT_MENTORING_SELECT_HINT=Select or type a {0}... |  |  | Amy Chen |  | 6 | 6 | TK-397211 | 6 | 2017-02-17
Amy Chen | 14 QA-add more space between discription and avilability control |  | Fit&Finish |  |  | Amy Chen |  | 2 | 2 | TK-397355 | 2 | 2017-03-01
Amy Chen | 16 QA-No Activity created yet should be in liter grey- Mentor |  | Fit&Finish |  |  | Amy Chen |  | 2 | 2 | TK-397357 | 2 | 2017-03-01
Amy Chen | 17 QA-No Activity created yet should be in liter grey- Mentee |  | Fit&Finish |  |  | Amy Chen |  | 2 | 2 | TK-397358 | 2 | 2017-03-01
Amy Chen | 18 QA-Choose different mentor beside the Activity Plan |  | Fit&Finish |  |  | Amy Chen |  | 2 | 2 | TK-397359 | 2 | 2017-03-01
Clark Lang | [6 empty] | 95.2 | 95 | 89
Clark Lang | Automation Test |  |  |  |  | Clark Lang |  |  |  | B-96036
Clark Lang |  | Automation Test | Automation Test |  |  | Clark Lang |  | 29 | 29 | TK-396924 | 29
Clark Lang |  | Pick&Refine automation test cases | Automation Test |  |  | Clark Lang |  | 6 | 6 | TK-396927 | 6
Clark Lang |  | CC | Automation Test |  |  | Clark Lang |  | 30 | 30 | TK-396943 | 30
Clark Lang |  | Automate Test case | Automation Test |  |  | Clark Lang |  | 30 | 24 | TK-396944 | 24
Haiyun Jiang | [6 empty] | 95.2 | 101 | 101
Haiyun Jiang | QA - Test Design |  | ATL for Mentor Sign Up Pages |  |  | Haiyun Jiang |  | 12 | 12 | TK-396794 | 12 | 2017-02-21
Haiyun Jiang | QA - Execution |  | ATL for Mentor Sign Up Pages |  |  | Haiyun Jiang |  | 13 | 13 | TK-396800 | 13 | 2017-02-21
Haiyun Jiang | QA -Design |  | RTL for Mentor Sign Up Pages |  |  | Haiyun Jiang |  | 3 | 3 | TK-396805 | 3 | 2017-02-21
Haiyun Jiang | QA - Execution |  | RTL for Mentor Sign Up Pages |  |  | Haiyun Jiang |  | 8 | 8 | TK-396811 | 8 | 2017-02-21
Haiyun Jiang | QA - Design |  | Programmatically Schedule Job |  |  | Haiyun Jiang |  | 6 | 6 | TK-397158 | 6 | 2017-02-17
Haiyun Jiang | QA - Execution |  | Programmatically Schedule Job |  |  | Haiyun Jiang |  | 12 | 12 | TK-397159 | 12 | 2017-02-17
Haiyun Jiang | ATL/RTL Rampup |  | ATL/RTL Rampup | [7 empty] | 9
Lily (Xiaoxin) Wu | [6 empty] | 60 | 50 | 50
Lily (Xiaoxin) Wu | Customer issue support - Lily |  | Unplanned Tasks |  |  | Lily (Xiaoxin) Wu |  | 12 | 12 | TK-396919 | 12
Lily (Xiaoxin) Wu | Pick&Refine automation test cases |  | Automation Test |  |  | Lily (Xiaoxin) Wu |  | 6 | 6 | TK-396926 | 6
Lily (Xiaoxin) Wu | QA Automation Env setup - Lily |  | Planned Tasks |  |  | Lily (Xiaoxin) Wu |  | 20 | 20 | TK-397738 | 20
Lily (Xiaoxin) Wu | XPI tasks go through |  | Planned Tasks |  |  | Lily (Xiaoxin) Wu |  | 12 | 12 | TK-397740 | 12
Lina Xiao | [6 empty] | 95.2 | 76 | 76
Lina Xiao | QA - Design |  | ATL for Mentee Sign Up Pages |  |  | Lina Xiao |  | 15 | 15 | TK-396814 | 15 | 2017-02-28
Lina Xiao | QA - Execution |  | ATL for Mentee Sign Up Pages |  |  | Lina Xiao |  | 18 | 18 | TK-396815 | 18 | 2017-02-28
Lina Xiao | QA - Design |  | RTL for Mentee Sign Up Pages |  |  | Lina Xiao |  | 5 | 5 | TK-396816 | 5 | 2017-02-27
Lina Xiao | QA - Execution |  | RTL for Mentee Sign Up Pages |  |  | Lina Xiao |  | 12 | 12 | TK-396817 | 12 | 2017-02-27
Lina Xiao | QA - Design |  | Mentor Home page: Better to have indication for a completed program |  |  | Lina Xiao |  | 3 | 3 | TK-396851 | 3 | 2017-02-13
Lina Xiao | QA - Execution |  | Mentor Home page: Better to have indication for a completed program |  |  | Lina Xiao |  | 3 | 3 | TK-396853 | 3 | 2017-02-13
Lina Xiao | QA - Design |  | Mentee Home page: Better to have indication for a completed program |  |  | Lina Xiao |  | 3 | 3 | TK-396860 | 3 | 2017-02-10
Lina Xiao | QA - Execution |  | Mentee Home page: Better to have indication for a completed program |  |  | Lina Xiao |  | 3 | 3 | TK-396862 | 3 | 2017-02-10
Lina Xiao | ATL/RTL Rampup |  | ATL/RTL Rampup | [7 empty] | 9
Lina Xiao | 1 QA - Give more space between ui elements under each section |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397340 | 2
Lina Xiao | 2 QA-Delete “previous” button and “save&launch” button？ |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397341 | 2
Lina Xiao | 9 QA-Add back button |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397350 | 2
Lina Xiao | 13 QA-Add back button |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397354 | 2
Lina Xiao | 19 QA-Program title (Link) should be in bold |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397360 | 2
Lina Xiao | 20 QA-Card action button should be wide |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397361 | 2
Lina Xiao | 21 QA-icon (matching icon) needs to be enhanced (design enhancements) |  | Fit&Finish |  |  | Lina Xiao |  | 2 | 2 | TK-397362 | 2
Mansur Ma | [6 empty] | 72.8 | 71 | 71
Mansur Ma | QA - Design |  | UI Consistency on Learning activities |  |  | Mansur Ma |  | 12 | 12 | TK-397149 | 12 | 2017-03-01
Mansur Ma | QA - Execution |  | UI Consistency on Learning activities |  |  | Mansur Ma |  | 15 | 15 | TK-397151 | 15 | 2017-03-01
Mansur Ma | QA - Execution(ATL) |  | UI Consistency on Learning activities |  |  | Mansur Ma |  | 6 | 6 | TK-397152 | 6 | 2017-03-01
Mansur Ma | SUPT - Mansur |  | Planned Tasks |  |  | Mansur Ma |  | 18 | 18 | TK-397405 | 18
Mansur Ma | QA Automation Env setup - Mansur |  | Planned Tasks |  |  | Mansur Ma |  | 20 | 20 | TK-397739 | 20
Stella Gao | [6 empty] | 72.8 | 45 | 41
Stella Gao | EAP - Stella |  | Planned Tasks |  |  | Stella Gao |  | 3 | 3 | TK-396917 | 3
Stella Gao | Customer issue support - Stella |  | Unplanned Tasks |  | In-progress | Stella Gao |  | 12 | 12 | TK-396920 | 12
Stella Gao | Add test case id for closed defects |  | Planned Tasks |  |  | Stella Gao |  | 6 | 6 | TK-397337 | 6
Stella Gao | Writing navigation document for atl team |  | Planned Tasks |  | Completed | Stella Gao |  | 4 | 0 | TK-397339 | 0
Stella Gao | QA Automation Env Setup - Stella |  | Planned Tasks |  |  | Stella Gao |  | 20 | 20 | TK-397737 | 20
Sunway Li | [6 empty] | 95.2 | 80 | 80
Sunway Li | Customer issue support - Sunway |  | Unplanned Tasks |  |  | Sunway Li |  | 6 | 6 | TK-396918 | 6
Sunway Li | Automation Function Review |  | Planned Tasks |  |  | Sunway Li |  | 6 | 6 | TK-396922 | 6
Sunway Li | QA - Design |  | Mentoring Dates to support i18N: Unavailable end date and program dates should consider different time zone different |  |  | Sunway Li |  | 9 | 9 | TK-397142 | 9 | 2017-02-08
Sunway Li | QA - Execution |  | Mentoring Dates to support i18N: Unavailable end date and program dates should consider different time zone different |  |  | Sunway Li |  | 12 | 12 | TK-397143 | 12 | 2017-02-08
Sunway Li | QA - Design |  | Adopt to new field PERSON_GUID in rest api /learning/delete |  | In-progress | Sunway Li |  | 9 | 9 | TK-397198 | 9 | 2017-02-20
Sunway Li | QA - Execution |  | Adopt to new field PERSON_GUID in rest api /learning/delete |  |  | Sunway Li |  | 6 | 6 | TK-397199 | 6 | 2017-02-20
Sunway Li | QA - Test Design & Execution |  | Update CDP Logic to consume Person-Based Learning API information |  |  | Sunway Li |  | 12 | 12 | TK-397203 | 12 | 2017-03-01
Sunway Li | QA Automation Env setup - Sunway |  | Planned Tasks |  |  | Sunway Li |  | 20 | 20 | TK-397736 | 20 | 2017-03-01
Yvonne Yu | [6 empty] | 89.6 | 85 | 85
Yvonne Yu | QA - Design |  | CDP-5778 Show Free Text Answers to Mentor |  |  | Yvonne Yu |  | 13 | 13 | TK-396831 | 13 | 2017-02-28
Yvonne Yu | QA - Execution |  | CDP-5778 Show Free Text Answers to Mentor |  |  | Yvonne Yu |  | 15 | 15 | TK-396832 | 15 | 2017-02-28
Yvonne Yu | QA - Design |  | CDP-5778 Show Free Text Answers to Mentee |  |  | Yvonne Yu |  | 8 | 8 | TK-396838 | 8 | 2017-02-27
Yvonne Yu | QA - Execution |  | CDP-5778 Show Free Text Answers to Mentee |  |  | Yvonne Yu |  | 8 | 8 | TK-396839 | 8 | 2017-02-27
Yvonne Yu | QA - Design |  | Ad hoc report change for open-ended program |  |  | Yvonne Yu |  | 9 | 9 | TK-396911 | 9 | ?
Yvonne Yu | EAP - Yvonne |  | Planned Tasks |  |  | Yvonne Yu |  | 6 | 6 | TK-396916 | 6
Yvonne Yu | Critical customer template - Yvonne |  | Planned Tasks |  |  | Yvonne Yu |  | 6 | 6 | TK-397408 | 6
Yvonne Yu | QA Automation Env setup - Yvonne |  | Planned Tasks |  |  | Yvonne Yu |  | 20 | 20 | TK-397735 | 20
Task
Test Design
Test Execution
Leave/Others(Meeting)